## Sheet1
Task | Start Date | End Date | Duration | Notes
Concept Creation | 2020-07-29 | 2020-08-01 | 3 | Figuring out a concept for the project
Concept Scope | 2020-08-01 | 2020-08-04 | 3 | Suiting the concept to the constraints
Finding Platform | 2020-08-04 | 2020-08-06 | 2 | Finding a suitable platform/ language for the concept
Creating Grid | 2020-08-06 | 2020-08-08 | 2 | Creating User Grid
Logic of Grid | 2020-08-08 | 2020-08-12 | 4 | Finding a way of calling cells
Grid Click Event | 2020-08-12 | 2020-08-14 | 4 | Finding a way to click cells to trigger event
Different Boats / Boat Logic | 2020-08-14 | 2020-08-18 | 4 | adding all the boats of battleship
Storing System | 2020-08-18 | 2020-08-22 | 4 | Way fo storing the current User grid layout
Checking Storage System | 2020-08-22 | 2020-08-24 | 4 | Way of checking the location of boats in the grid
Enemy Grid | 2020-08-20 | 2020-08-22 | 2 | Making enemy grid
Enemy Turn | 2020-08-22 | 2020-08-25 | 3 | Adding the enemies guess and verifying results.